## GHSP Supplier SREA
SUPPLIER TO COMPLETE | [12 empty] | Yes
SUPPLIER NAME AND ADDRESS: | [7 empty] | SUPPLIER CONTACT NAME / TITLE: |  |  |  |  | No
SUPPLIER PHONE / E-MAIL:
GHSP PART NUMBER(s): | [6 empty] | GHSP DRAWING NUMBER/REVISION:
PROPOSED/MARKED DRAWING ATTACHED? | [8 empty] | DATE REQUESTED:
SPECIAL CHARACTERISTIC AFFECTED (GHSP / SUPPLIER)?
SELECT GHSP SITE(S) THAT ARE DIRECTLY IMPACTED:
| Grand Haven |  | Hart |  |  | Saltillo |  |  | Shanghai North |  |  | Shanghai South
DESCRIPTION OF PROPOSED CHANGE (check all that apply)
| Supplier Manufacturing Location Change | [5 empty] | New or Additional Tooling |  |  | Alternate Material
| Supplier Proposed Engineering/Design Change | [5 empty] | Sub-supplier Change |  |  | Sub-supplier Location Change
| Supplier Manufacturing Process Change | [5 empty] | Other: |  |  | Supplier Shipping Location Change
REASON(S) FOR PROPOSED CHANGE
| Fit | Form |  |  | Function |  |  |  | Best Practices/Improvements
| Cost Reduction |  |  |  | Appearance |  |  |  | Corrective Action (PTR#):
DETAILED DESCRIPTION OF CHANGE (Timing plan and validation plan required - see additional tabs)
Requested change must include a detailed Safe Launch Containment Plan. Copy to SAFE LAUNCH tab.
Tool Change Required?
Piece Cost Affected? If yes, NET piece cost effect $
Bank/Inventory Required ?(include in timing plan)
Total Timing Required to Incorporate Change After Approval (in weeks): | [10 empty] | weeks
BELOW SECTION FOR GHSP TO COMPLETE
GHSP LOG #
SUPPLY CHAIN REPRESENTATIVE RESPONSE TO THE CHANGE PROPOSAL:
| Approve |  |  |  |  | Reject |  |  |  | Need More Information
Feedback to Supplier (required if Reject or Need More Information):
Approval (Printed Name): | [9 empty] | Date:
PRINCIPAL ENGINEER RESPONSE TO THE CHANGE PROPOSAL (except packaging):
PROCESS ENGINEER RESPONSE TO CHANGE PROPOSAL (packaging only)
| Approve |  |  |  |  | Reject |  |  |  | Need More Information
Unless otherwise specified line trial parts required | [5 empty] | QTY
Feedback to Supplier (required if Reject or Need More Information):
Component drawing to be updated? |  |  |  | Yes | No |  | Customer drawing requiring update?
Approval (Printed Name): | [9 empty] | Date:
QUALITY ENGINEER RESPONSE TO THE CHANGE PROPOSAL:
| Approve |  |  |  |  | Reject |  |  |  | Need More Information
Unless otherwise specified line trial parts required | [5 empty] | QTY
Feedback to Supplier (required if Reject or Need More Information):
PPAP required to customer? |  |  |  | Yes | No |  | Customer change approval required?
Approval (Printed Name): | [9 empty] | Date:
BUYER RESPONSE TO THE CHANGE PROPOSAL (COST CHANGE ONLY):
| Approve |  |  |  |  | Reject |  |  |  | Need More Information
Feedback to Supplier (required if Reject or Need More Information):
Approval (Printed Name): | [9 empty] | Date:
FINAL PLAN APPROVAL
Approval (Printed Name): | [9 empty] | Date:
* This approval is granted upon the understanding that it is advisory in nature and in no manner changes the Sellers original responsibility for ensuring that all characteristics, designated in the applicable engineering specification and/or inherent in the samples as originally tested and approved, are maintained. Seller accepts full responsibility for the changes or types of changes listed above; and should such changes result in less satisfactory performance than experienced with the originally approved item, Seller will fully reimburse GHSP for all expenses incurred to correct the deficiency.
Also note that by submitting this form, Supplier conveys ownership of the submitted suggestion to GHSP.
Yes
Yes
No
No

## Timing Plan
PROJECT NAME: |  | Remove Assembly Step
PROJECT DEPT: |  | Supplier A
PROJECT LEADER: |  | Jane Doe | [11 empty] | Plan
Actual
ACTION |  |  | ACTION DATES
ACTIVITY | Duration | RESP | PLAN START | PLAN DUE | ACTUAL START | ACTUAL END | Detailed Sched Link | Pln vs Act | 2016-04-06 | 2016-04-13 | 2016-04-20 | 2016-04-27 | 2016-05-04 | 2016-05-11 | 2016-05-18 | 2016-05-25 | 2016-06-01 | 2016-06-08 | 2016-06-15 | 2016-06-22 | 2016-06-29 | 2016-07-06 | 2016-07-13 | 2016-07-20 | 2016-07-27 | 2016-08-03 | 2016-08-10 | 2016-08-17 | 2016-08-24 | 2016-08-31 | 2016-09-07 | 2016-09-14 | 2016-09-21 | 2016-09-28 | 2016-10-05 | 2016-10-12 | 2016-10-19 | 2016-10-26 | 2016-11-02 | 2016-11-09 | 2016-11-16 | 2016-11-23 | Comment | Detail | Other
Team Collaboration Mtg |  |  | 2016-04-13 | 2016-04-27 |  |  |  | P | bar: 2016-04-13 to 2016-04-20
A
Lesson learned review |  |  | 2016-04-14 | 2016-04-28 |  |  |  | P | bar: 2016-04-13 to 2016-04-20
A
Create timeline |  |  | 2016-04-13 | 2016-04-27 |  |  |  | P | bar: 2016-04-13 to 2016-04-20
A
Submit SREA to GHSP |  |  | 2016-04-27 | 2016-05-04 |  |  |  | P | bar: 2016-04-27
A
SREA Plan Approval | 5 wks |  | 2016-05-04 | 2016-06-10 |  |  |  | P | bar: 2016-05-04 to 2016-05-25
A
Build parts with the change |  |  | 2016-05-04 | 2016-06-01 |  |  |  | P | bar: 2016-05-04 to 2016-05-18
A
Mature production process of change |  |  | 2016-05-04 | 2016-06-01 |  |  |  | P | bar: 2016-05-04 to 2016-05-18
A
Supplier PV testing |  |  | 2016-06-01 | 2016-06-08 |  |  |  | P | bar: 2016-06-01
A
Submit PPAP for Review & Approval (See AIAG Requirements) |  |  | 2016-06-08 | 2016-06-29 |  |  |  | P | bar: 2016-06-08 to 2016-06-22
A
Safety Stock Bank Build Review (If Applicable) |  |  | N/A |  |  |  |  | P
A
GHSP Testing (if applicable) | 6-12 wks |  | 2016-06-29 | 2016-08-24 |  |  |  | P | bar: 2016-06-29 to 2016-08-17
A
Customer Approval | 4 wks |  | 2016-08-24 | 2016-09-21 |  |  |  | P | bar: 2016-08-24 to 2016-09-14
A
Final approval | 2 wks |  | 2016-09-21 | 2016-10-05 |  |  |  | P | bar: 2016-09-21 to 2016-09-28
A
SOP | [7 empty] | P
A
GHSP rough planning guidelines. Must be included in supplier timeline.
Example. This is meant to be a template for your reference. Please provide a detailed timeline with SREA

## Validation Plan
Validation Plan will tell GHSP how you plan to assess conformance (acceptance criteria) of the change proposal
Outline what the plan is and how many parts will be checked for compliance
Deliverable | YES | NO | If "NO", why? / If "YES" provide quantity or other details about submission.
Design Records - Ballooned Drawing
Engineering Change Document
Customer Engineering Approval
DFMEA
Process Flow
PFMEA
Dimensional Results
Material Performance Test Results
Initial Process Study
Measurement System Analysis
Laboratory Documentation
Pre-Launch or Safe Launch Control Plan
Production Control Plan
PSW
AAR
Bulk Material Checklist
Sample Product
Master Sample
Checking Aids
Records of Compliance with Customer Spec Reqs
Signed DFS Form
Approved Packaging Sketch Form
PSO
Tooling and Gauge Form
Timeline
PPAP Checklist
Container Label
IMDS Report
Country of Origin
Other
Plant Layout / Geographical Map
Poke Yoke Verification
Preventative Maintenance Plan
Change Point Identification
Spare Parts Plan
Equipment Type
Note on C8: Ballooned drawing must be included with dimensional layout or if design record is being changed.
Note on C11: Does the DFMEA need to be updated? Summary of changes should be provided or line items highlighted.
Note on C12: Will the process flow be changing? Summary of changes should be provided or line items highlighted.
Note on C13: Does the PFMEA need to be updated? Summary of changes should be provided or line items highlighted.
Note on C14: A - B comparison should be provided. Quantity depends on process and tooling.
Note on C15: Material certification must be provided for a sub-supplier of material change. Additional testing should be considered if an assembly is provided.
Note on C16: A - B comparison should be provided. Quantity and features depend on process, tooling and drawing requirements.
Note on C17: Gauge R&R must be considered if the measurement method or part has a significant change.
Note on C18: ISO/TS, IATF or any other organizational certifications must be considered with a sub-supplier change.
Note on C19: Does the requested change require a safe launch / flawless / GP12 operation?
Note on C20: Does the control plan need to be updated? Summary of changes should be provided or line items highlighted.
Note on C21: An updated PSW is requred for all changes.
Note on C22: Must be provided for sub-supplier, equipment or material changes.
Note on C25: Will the master PPAP samples be changing or updated with additional components?
Note on C26: Will updates to check fixtures or gauges be required?
Note on C28: Changes to any characteristic designation or measurment method on those features need to be addressed with an updated DFS form.
Note on C29: Are there any packaging changes? All changes will need to be approved by GHSP.
Note on C30: PSO form should be considered to ensure changes are still meeting expectations.
Note on C31: Were updates to the tooling or gauge made that require updated tags, part number or revision changes.
Note on C32: Estimated timeline must be provided on the "Timing Plan" slide. All timing is subject to change.
Note on C33: Should be considered if there is concern with not meeting GHSP requirements the first time.
Note on C34: Label sample is required for any changes to the data on the label
Note on C35: Must be re-submitted for part number, sub-supplier or material changes.
Note on C36: Must be submitted if country of manufacture is changing.
Note on C38: Visual explaination of where machines or facility will be located.
Note on C39: List of red rabbits / start up parts and verification of function must be completed for sub-supplier, equipment and process changes.
Note on C40: Should be considered for changes to sub-supplier or equipment changes.
Note on C41: Will a change point need to be identified and what will that be.
Note on C42: An analysis and list of long lead time and high risk parts should be considered if there is a new sub-supplier or equipment change.
Note on C43: Details for equipment must be provided for a manufacturing change or sub-supplier change.
Example for reference only. Please Complete

## SAFE LAUNCH
Safe Launch Plan must be submitted by supplier prior to SREA Approval. Example template is below
Part #
Description
Item # | Feature to be re-inspected out of the Production Cell | CRITERIA/INSPECTION METHOD | Inspection frequency | Exit Criteria | Has control plan been updated to reflect safe launch?

## REQUIREMENTS
This is what we need to be prepared to present our customer in order to gain approvals.
Slide # 1-2 | Deliverable / Validation Plan | Sub-Supplier Change (new/ additional) | Equipment Change | Geographical Location Change | Material Change | Equipment Move | Process Change
3 | Purpose of the Change (Benefits) | X | X | X | X | X | X
4 | Affected Components | X | X | X | X | X | X
5 | Change Point and Risk Identification Analysis | X | X | X | X | X | X
6 | Validation Plan | X | X | X | X | X | X
7 | Who are the new suppliers current customers? | X
8 | Completed GHSP Supplier Assessment | X
9 | ISO/TS Certs | X
10 | Material Certs (Current vs New) | X |  |  | X
11 | Dimensional Analysis (Pre vs Post, Current vs New) | X | X | X | X | X | X
12 | Dimensional confirmation by GHSP (smaller sample size) | X | X | X | X | X | X
13 | Map Location (Pre vs Post, Current vs New) | X |  | X
14 | Current process vs future process description w/ supporting data | X | X | X | X | X | X
15 | Capacity | X | X | X | X | X | X
16-17 | Capability (Pre vs Post / Current vs New) on all SC's/CC's - 125pcs per cavity (1.67 CPK) | X |  |  | X |  | X
16-17 | Capability (Pre vs Post / Current vs New) on all SC’s/CC’s – 30 pcs per cavity per tool (125pcs minimum total, more if data warrants it) (1.67 CPK) |  | X | X | X | X | X
18-20 | Gage R&R's | X | X | X |  | X
21 | Updated Process Flow w/ sequence of operations changes (summarizing pre and post changes, if applicable) | X | X | X | X | X | X
22-23 | Updated plant layout current vs new |  | X | X |  | X | X
24 | Updated PFMEA (summarizing pre and post changes, if applicable) | X | X |  | X |  | X
25 | Updated Control Plan (summarizing pre and post changes, if applicable) | X | X |  | X |  | X
26 | Material Handling plan | X |  | X |  | X | X
27 | Lot number format and methodology | X |  |  | X
28 | PV Test Plan | X | X |  | X |  | X
29 | Poke Yoke(RED RABBIT/START UP) list w/verification | X | X |  |  | X | X
30 | Equipment Type | X | X
31 | Spare Parts Plan | X | X
32 | PM Plan | X | X
33 | Packaging | X |  | X
34 | FTT (First Time Through) data (measured as the percentage of product that successfully passes through the process its first time through) | X | X |  | X | X | X
35 | Safe Launch / Flawless Launch Plan @ all tiers | X | X | X | X | X | X
36 | GHSP Incoming Inspection plan | X | X | X | X | X | X
37 | Time line | X | X | X | X | X | X
GHSP has a supplemental powerpoint presentation, SREA Overview, that is available on the GHSP Website for suppliers to utilize to document the plan and provide supporting documentation for this change.

## Revisions
Revised Date | Form Change
2018-10-23 | Revised the entire form to meet our customer requirements